## Sheet1
OMG-EDMC Standard
Work stream | Description | Activity | Tasks | Deliverable (Release, Format…) | Timeline | Applicable Industry Standard, Best Practices, (OMG, ISO…) | WG Lead's Contact Info | WG Members' Contact Info | Comments
EDMC Semantic repository Content (a.k.a. Semantic Models for financial reform standard) | Set of technology agnostic vocabulary and models suitable for business user audience
|  | Validate and refine industry standards* based business Vocabulary for Legal Entity Identifier, Product Hierarchy, Time, Date (and other concepts in Release 1) | Identify external vocabularies that can be used to enrich Release 1 (ISO15022, FIX, FPML…) | Release 1 1. Request for Comment (RFC) Document containing the business Vocabulary 2. Web based access (read, write) to business vocabulary via model management repository (see model management work stream for details) 3. XMI Format for interchange with other tools | Q4, 2011 (end) | 1. * OMG Semantics of Business Vocabulary and Rules 2. Enriched with concepts from FIX, FPML, ISO15022 |  |  | 1. After validation by OMG-EDMC team, need to socialize with makers of FIX, FPML, ISO15022, SWIFT…
Import current EDMC vocabulary (Excel) into SBVR compliant tool
Export and manage vocabulary in model management repository
|  | Validation and enrichment of Legal Entity Hierarchy model | Validate and enrich model content (entities, attributes, relationships, cardinality) with business SMEs - Identify additional legal entity concepts from other standards as applicable | Release 1 - Legal Entity Hierarchy Model - XMI, ODM/OWL format | Q1, 2012 | 1. OMG Ontology Definition Metamodel (ODM) 2. Ontology Web language (OWL) 3. OMG Information Management Metamodel (IMM)
Validate model conformance to guidelines, procedures defined in Modeling Framework deliverables with modeling standards experts
|  | Validation and enrichment of Product Hierarchy Model | Validate and enrich model content (entities, attributes, relationships, cardinality) with business SMEs - Identify additional legal entity concepts from other standards as applicable | Release 1 - Product Hierarchy Model - XMI, ODM/OWL format | Q1, 2012
Validate model conformance to guidelines, procedures defined in Modeling Framework deliverables with modeling standards experts
|  | Validation and enrichment of business critical classification of Vocabulary Terms and model attributes | Validate and enrich classifications to meet regulatory compliance and other future needs | Release 1 - Approved Business Critical Classification document (Excel)
Modeling Framework | A modeling framework that consists of modeling best practices, guidelines, existing OMG and other modeling languages to allow complete life-cycle management and traceability of business vocabularies and models in scope | Enhancements to the modeling languages used in the development of the OMG-EDMC Standard | Evaluate and align with the ODM standard (including any enhancements needed) | Release 1 - Framework of core and specialized modeling languages and traceability concepts - Intersection met model for OMG-EDMC standard? - List and classification? of Namespaces (managed in model management repository?)
Enhancements to, alternatives to, modifications of OWL (Ontology Web Language)
Management of Namespace and archetypes (alignment)
SBVR – mapping of SBVR content with the Semantics Repository (what exists within SBVR that can be leveraged)
Standard availability and access management | Process, versioning and availability (access control) of the OMG-EDMC standard components (vocabulary, models, interchange formats etc.) using a Model Mgmt Repository- MMR (a.k.a. metadata repository) | Define, validate and approve the Process, Policies and Procedures by which makers and consumers of the deliverables will have access (read, write/update) to the standards artifacts | Develop Process, Policies and Procedure document - Key dependencies (and timing of each) - Relationship with repository and tool providers (contractual) | Release 1 - Web based vocabulary access in MMR | Q4, 2011
Identify Roles (access) to the repository content
|  |  | Upload and manage (version control, check in/out) Business Vocabulary (Excel and other tools) | Release 2 - Models and reports available in MMR | Q1, 2012
Upload and manage (version control, check in/out) semantic models: from modeling tool(s)
Develop and manage major traceability relationships/report (vocabulary, model reports etc.)
Standard Governance (Process, Policies and Procedures) | Governance model for the complete life-cycle of the proposed standard (define, develop, adopt and maintain...) | Define how the EDMC/OMG standards development process will be managed | 1. Decision making process (and method of redress) 2. Process, policies and procedures that exist within OMG (how we work within the OMG environment) including any processes that already exist to align standard with regulatory requirements 3. Management of the development process (how work streams are formed, how people participate, how leadership is managed) 4. Development of work plans with time frames for delivery 5. Versioning and control of output of work streams 6. Resourcing strategy (how resources are acquired and funded) 7. Groups liaison (how EDMC/OMG interact with other related groups) 8. Logistics of development (i.e. management of database of engaged individuals, rules for engagement, distribution of materials) | Release 1 Governance Model | Q2, 2011 (end) | OMG Policies and Procedures | Andrew Watson, OMG Director of Policies and Procedures and Adoption Process | Andrew Watson, additional OMG resource, Harsh Sharma, Mike Bennett, ?
Advocacy (Positioning and Communication, buy-in...) | Advocacy of the Business value of the standard to the makers and consumers of financial reform regulations | Define how we define, validate and communicate the objectives of the initiative; obtain stakeholder buy-in, participation | 1. White paper on approach (strategy validation and definition of critical ingredients for success) 2. Business case for the standard (costs and benefits) 3. Relationship to regulatory objectives and how we interact with regulators (requirements capture and validation) 4. Name of standard (and how it is described to full spectrum of stakeholders) | Release 1 1. Advocacy strategy 2. White paper on sustainable strategy, framework of critical ingredients for success | Q3, 2011 end |  |  |  | Business case task is TBD as it will involve extensive research, funding and involvement of resources outside OMG-EDMC group.
Training and Certification | Training on use of the standard and certification for regulatory reporting compliance? | Define the training and certification objectives |  | Release 1 1. Training materials 2. Certification process and materials | Q2, 2012 |  | OMG, EDMC